## Executive Dashboard
Metric | Target | Current
Project Completion | 100% | 0%
Weeks | 4 | 0
Open Risks | <5 | 0
Services Deployed | 4 | 0
Clusters Ready | 2 | 0

## 4 Week Plan
Week | Objective | Deliverables | Status
Week 1 | Infrastructure | Terraform, AWS EKS, Azure AKS, IAM, Networking, Git | In Progress
Week 2 | Containers & K8s | NodeJS Apps, Docker, Kubernetes, Helm | Not Started
Week 3 | Observability & CI/CD | Prometheus, Grafana, Loki, GitHub Actions, Jenkins | Not Started
Week 4 | GitOps & Auto-Healing | ArgoCD, HPA, Rollbacks, Jira, Slack, Documentation | Not Started

## Day Wise Planning
Day | Week | Task | Deliverable | Planned Hours | Status | Comments
1 | Week 1 | Create GitHub Repositories | Repos Created | 4 | In Progress | https://github.com/vkharishb/Multi-Cloud-Kubernetes-Auto-Healing-Auto-Scaling-Platform.git
2 | Week 1 | Terraform Project Structure | Folders & Modules | 6 | In Progress
3 | Week 1 | Provision AWS Networking | VPC/Subnets | 6 | Not Started
4 | Week 1 | Provision AWS EKS | Cluster Ready | 8 | Not Started
5 | Week 1 | Provision Azure Networking | VNET | 6 | Not Started
6 | Week 1 | Provision Azure AKS | Cluster Ready | 8 | Not Started
7 | Week 1 | IAM & Validation | Access Tested | 4 | Not Started
8 | Week 2 | Create NodeJS user-service | Code Ready | 6 | Not Started
9 | Week 2 | Create order-service | Code Ready | 6 | Not Started
10 | Week 2 | Dockerize Services | Dockerfiles | 6 | Not Started
11 | Week 2 | Kubernetes Deployments | Deployments YAML | 6 | Not Started
12 | Week 2 | Services & Ingress | Ingress Working | 6 | Not Started
13 | Week 2 | Helm Charts | Chart Ready | 6 | Not Started
14 | Week 3 | Install Prometheus | Metrics Available | 4 | Not Started
15 | Week 3 | Install Grafana | Dashboards Ready | 4 | Not Started
16 | Week 3 | Install Loki | Logs Visible | 4 | Not Started
17 | Week 3 | GitHub Actions Pipeline | CI Ready | 6 | Not Started
18 | Week 3 | Jenkins Pipeline | CD Ready | 6 | Not Started
19 | Week 4 | Install ArgoCD | GitOps Ready | 4 | Not Started
20 | Week 4 | Create Argo Applications | Sync Working | 4 | Not Started
21 | Week 4 | Configure HPA | Scaling Tested | 4 | Not Started
22 | Week 4 | Configure Rollbacks | Rollback Tested | 4 | Not Started
23 | Week 4 | Slack Integration | Alerts Working | 3 | Not Started
24 | Week 4 | Jira Integration | Tickets Created | 3 | Not Started
25 | Week 4 | Testing | UAT Complete | 6 | Not Started
26 | Week 4 | README & Docs | Documentation Complete | 6 | Not Started
27 | Week 4 | Resume Updates | Resume Points Added | 2 | Not Started
28 | Week 4 | Final Demo | Project Closure | 2 | Not Started

## Sprint Tracker
Sprint | Goal | Status

## Backlog
ID | Task | Priority | Status

## RAID Log
Type | Description | Owner | Status

## Milestone Tracker
Milestone | Target | Status
AWS EKS Ready | End Week 1 | Not Started
AKS Ready | End Week 1 | Not Started
Apps Containerized | End Week 2 | Not Started
Monitoring Ready | End Week 3 | Not Started
GitOps Ready | Week 4 | Not Started
Project Complete | Week 4 | Not Started

## Weekly Status Report
Week | Completed | In Progress | Blocked | Next Week Plan